## 工作表1
Task Category | Task # | Task Description | Estimated Manday(s) | Assignee | % Completion
Project Initiation
|  | Copy | 2 | Joe | 0
|  | Edit |  | Joe | 0
|  | Extension |  | Joe | 0
|  | Print Project Record | 2 | Joe | 0
Validate Payment | Enquiry
|  | Interface |  | Troy | 100
|  | List Payment Request |  | Troy | 90
|  | Apply Search Criteria |  | Troy | 30
|  | Create sub batch button |  |  | 0
New Batch
|  | Interface |  | Troy | 100
|  | Create new request |  | Joe | 0
|  | Redirect page to Edit mode |  | Joe | 100
|  | Download excel template |  | Sandeep | 80
New Sub Batch
|  | Interface |  | Troy | 100
|  | Create a new request |  | Troy | 0
|  | Parent request's on-hold record redirect to new Request |  | Troy | 0
|  | Once create new request, reset on-hold total to 0 of parent request |  | Troy | 0
|  | Download excel template with parent request's on-hold record |  | Sandeep | 80
Edit
|  | Interface |  | Sandeep | 100
|  | Submit request |  | Sandeep | 0
|  | If no record, disable submit button |  | Sandeep | 0
|  | Click edit button can download the template with details record |  | Sandeep | 0
|  | Upload template |  | Sandeep | 90
|  | Process validation of updated file |  | Sandeep | 0
|  | New dialog to display error |  | Sandeep | 80
|  | Auto save if all record upload successful |  | Sandeep | 0
|  | If submitted record, disable upload, edit, submit button |  | Sandeep | 0
Transfer to HCM | Enquiry
|  | Interface |  | Troy | 100
|  | List Submitted request |  | Troy | 80
View/Edit
|  | Interface |  | Sandeep | 100
|  | Transfer to HCM (Pending) |  | Pending | 0
|  | Rollback Record |  | Sandeep | 0